| INSTITUTE Overall Health and Safety Plan Installation of the support structure for the LHCb Outer Tracking system INSTITUTE: Physikalisches Institut Universität Heideleberg Address: Philosophenweg 12, 69120 Heidelberg, Germany Tel: 06221/549336 Fax: 06221/475733 Email: Bachmann@physi.uni-heidelberg.de Starting date of the operation: Please note that a copy of this document must be kept on Site |  |
| --- | --- |
| Company /Institute Written by: Sebastian Bachmann Drawn up on: 22.3.2006 Sent on: | Received by the Co-ordinators TS/HDO on |

UPDATES

| Index | Date | Reasons for Revision |
| --- | --- | --- |

# A -	The general presentation and general organisation of the site

Institute: Physikalisches Institut, Universität Heidelberg

Profession:

Description of the operation to be carried out

Installation of the support structure for the LHCB Outer tracking system

| Period of execution | Effective |
| --- | --- |
| Start Date: 27.3.2006 | Average: |
| Completion Date: 30.5.2006 | Maximum: |

## 1 - 	SITE ADMINISTRATION

Site address: CERN CH – 1211 Geneva 23

Access to the site by point 8

All personnel should use the PM elevator to access the underground areas.

The Declaration Date For The Start Of The Work:

Authorisation to start work given on: 00/00/00

## 2-	THE ORGANISATION FOR THE APPLICATION OF THE OVERALL HEALTH AND SAFETY PLAN

|  | Recipient of the overall safety plan | Tel. | Fax |  |
| --- | --- | --- | --- | --- |
| Company Structure |  |  |  |  |
| Technical Coordinator for the Institute: Sebastian Bachmann.............................. His Role: Physicist | ###### X | 0041-22-767-5826 |  |  |
| CERN Works Engineer for the Institute | X | 0041-22-767- |  |  |
| Henk Schuiljenburg Role and means of carrying out his function |  | 6309 |  |  |
| Engineer |  |  |  |  |
| Site Manager CERN work supervisor for the Institute: Sebastian Bachmann | X | 0041-22-767-5826 |  |  |
| Manager responsible for security or CERN GLIMOS for the Institute | - |  |  |  |
| Assistance, in coordination and in charge of actions in relation to safety problems |  |  |  |  |

- PERSONS CONCERNED BY THE OVERALL HEALTH AND SAFETY PROTECTION PLAN

| Intervenants | Name | Address | Tel. | Fax | Email |
| --- | --- | --- | --- | --- | --- |
| Safety coordination CERN (TS/HDO) | Jean Weber Emmanuel Paulat John Etheridge | CERN Bat 112-4-C27 1211 Geneve 23 | 00-41-22-767-1384 00-41-76-487-4649 00-41-22-767-3262 00-41-76-487-3870 00-41-22-767-9936 00-41-76-487-4647 | 00-41-22-767-9104 | Jean.Weber@cern.ch Emmanuel.Paulat@cern.ch John.Etheridge@cern.ch |
| Maitre D’oeuvre CERN | Chef de group CERN or representative | CERN 1211 Geneva 23 |  |  |  |
| INSPECTION DU TRAVAIL (HSE work inspectorate) | Madam A. Grandjean. | 16,Place de la Grenouillère 01012 BOURG EN BRESSE Cedex | 04-74-45-91-39 | 04-74-45-33-52 |  |
| CRAM (Regional health insurance authority) | Monsieur J.P. Magnin | 35,rue Maurice Flandin 69003 | 04-72-91-96-96 | 04-72-91-97-09 |  |
| O.P.P.B.T.P. (Office of health and safety in the building and public works trade) | Monsieur B. Gavand | 2, Place Gailleton 69002 Lyon | 04-78-37-36-02 | 04-78-37-69-23 |  |
| DEAL (Site Inspectorate) | Monsieur J. C. Dutruel | 5, rue David Dufour CH-1205 Geneva | 022-327-40-70- | 022-328-75-52 |  |
| OCRIT (HSE Work Inspectorate) | Monsieur J. Malleret | 23, rue Ferdinland Holder C. P. 3974 1211 Geneva | 022-319-28-50 | 022-735-45-18 |  |
| SUVA | Monsieur R. Parvex | 158,Route d’Aire Case Postale 79 CH-1219 | 022-796-01-03 | 022-796-01-03 |  |
| Médecine du travail (Work Doctor) | Monsieur R. Strobel | CERN- Labo II Site de Prevessin BP 52 01631 CERN CEDEX | 00-41-22-767-5356 | 00-41-22-767-7610 |  |

## Please note a copy of the PPSPS must be sent to the above statutory bodies

## COMPANY AND EMPLOYEE INFORMATION

| Name/Surname | ###### Qualification / Instiitute | Certificates of Competence & Authorisation | Name of person with competent First Aid Skills | Special Medical Surveillance |
| --- | --- | --- | --- | --- |
| Bachmann, Sebastian | Physicist, Univ. of Heidelberg |  |  |  |
| Schuiljenberg, Henk | Engineer, Nikhef |  |  |  |
| Rummel, Christian | Technician, Univ. of Heidelberg |  |  |  |
| Rabenecker, Simon | Technician, Univ. of Heidelberg |  |  |  |
| Stumpf, Kevin | Technician, Univ. of Heidelberg |  |  |  |
| Fieser, Thomas | Technician, Univ. of Heidelberg |  |  |  |
| Ziegler, Ralf | Technician, Univ. of Heidelberg |  |  |  |
| Arink, Ruud | Technician, Nikhef |  |  |  |
| Band, Hans | Technician, Nikhef |  |  |  |
| Berbee, Edward | Technician, Nikhef |  |  |  |
| Ceelie, Loek | Technician. Nikhef |  |  |  |
| Pellegrino, Antonio | Physicist,Nikhef |  |  |  |
| Van Petten, Oscar | Technician, Nikhef |  |  |  |
| Spelt, Jan | Engineer, Nikhef |  |  |  |
| Tuning, Niels | Physicist, Nikhef |  |  |  |
| Haas, Tanja | Physicist, Univ. of Heidelberg |  |  |  |
| Knopf, Jan | Physicist, Univ. of Heidelberg |  |  |  |
| Deissenroth, Marc | Physicist, Univ. of Heidelberg |  |  |  |
| Albrecht, Johannes | Physicist, Univ. of Heidelberg |  |  |  |
| Blouw, Johan | Physicist, Univ. of Heidelberg |  |  |  |
| Wiedner, Dirk | Physicist, Univ. of Heidelberg |  |  |  |
| Uwer, Ulrich | Physicist, Univ. of Heidelberg |  |  |  |
| Corajod, Bernard | Technician, CERN |  | yes |  |
| Fournier, Cedric | Technician, CERN |  | yes |  |
| Chadaj, Bernard | Technician, CERN | Permission to work in height |  |  |
| Decreuse, Gerard | Technician, CERN | Permission to work in height |  |  |

## 5-	SUB CONTRACTORS (THIS PAGE DOES NOT CONCERN THE WORK PACKAGE CONTRACTORS OR INSTITUTES WHO CARRY OUT THE WORK THEMSELVES)

| Job | Company Name | Address | Responsible | Tel Fax Email | Start and Finish dates | Issues date of the Special Health and Safety Protection Plan | Co-activity |
| --- | --- | --- | --- | --- | --- | --- | --- |

## 6-	 SITE HEALTH AND SAFETY ORGANISATION

Health and Safety documents that must be kept on site:

*Staff Register:

*Register containing the observation made by Work Inspectorate and the

remedial action taken

*A register containing the visits made by preventive organisations

*A register containing the visits made by organisations in charge of technical

controls

*A copy of the certificate that states the employee is competent and medically

fit

*An up to date copy of the Special Safety and Health Protection Plan

Site signs and markings:

Site sings and markings are under CERN responsibility

See the document issued at the end of the special LEP Access briefing

7-	PARTICALE INFORMATION: RELATING TO FIRST AID AND EVACUATIONOF PERSONNEL

7.1. Emergency Telephone numbers

Method of communication

All emergency calls must be directed to the CERN Fire and Rescue Service

From internal CERN Telephones: Dial 112

From red Telephones: Direct

From a French portable telephone: Dial 00-41-22-767-444

Please us 00-41 from any Swiss Phone

7.2. SITE FIRST AID BOX

7.3. Occupational First Aider

Ever working team must have one occupational First Aider

Number of Occupational First Aider: 1

Name: Bernard Corajod

Means of identification:

7.4. What to do in the event of an accident

Instructions

Protection

Make sure there is no further danger: Protect yourself

If necessary stop the risk at source: Switch of the electricity, put out the fire…

Call the CERN Fire and Rescue Service

First Aider

Call the occupational First Aider

Non-serious accidents

The injured person shall be treated by one of the first aiders present on the work site

Serious accidents

The occupational first aiders will administrate whatever treatment they can, at the same time calling the CERN Fire and Rescue Service

Message to be given (clarity, brevity, and dispatch)

Here is the Physikalische Institut Heidelberg		Sector… Site Prevessin (F) Point 8

Nature of accident: 		Collision, Falling from height, and burns

Number of injured

Condition of the injured party or parties

7.5. Qualified Personnel

Name:

Surname:

Qualification:

Professional Training

1.1 - 	Method Statement

| Site:.Point 8......................................... . Work to be carried out: Installation of support structure of LHCb OT Trade:.......................................... Person Responsible Sebastian Bachmann |  | Form N° Written by Sebastian Bachmann. |
| --- | --- | --- |
| Work to be carried out WORK 1 | Transport of support structure from surface – SX 8 to UX85. Relevant technical drawings are attached to the document. Support structure consists of - Aluminium tables (Figure 1) consisting of 2 pieces, each made of approx. 350kg Envelope = 3500 x 1700 x 900 mm3 (see also LHS-120.dxf) 3 pieces, each weighting approx. 350kg: Envelope = 2500 x 800 x 600 mm3 (see also LHS-130.dxf) 3 pieces, each weighting approx. 350kg: Envelope = 2500 x 800 x 600 mm3 (see also LHS-140.dxf) 3 pieces, each weighting approx. 350kg: Envelope = 2350 x 800 x 600 mm3 (see also LHS-150.dxf) 3 pieces, each weighting approx. 350kg: Envelope = 4300 x 800 x 600 mm3 (see also LHS-160.dxf) - 2-feet Pillars (Figure 2): 1 piece weighing: approx. 750kg; Envelope = 8000 x 1500 x 400 mm3 - 4-feet Pillars (Figure 2): 2 pieces, each weighting: approx. 1500kg; Envelope = 8000 x 1500 x 1500 mm3 - Bridge (Figure 2): Total weight: 10 t; Envelope = 18000 x 2200 x 1600 mm3 Details for the fixation points for the bridge are given in figure 3. The handling of the bridge during the transport from SX8 to UX85 is described in detail in the documents bridge_handling1.pdf, bridge_handling2.pdf and bridge_handling3.pdf attached to this document. (For 2., 3., and 4. see also 05.200.69.0001.dwg) For handling of the materials are available - Pont roulant available at SX8 (80 tons) - Ponts roulants available at UX85 (2x40 tons) - Movable platform (100 tons) |  |
| Risks | 1.) General risks of handling heavy loads. 2.) Risk of materials to fall off during transportation with crane from SX8 to UX85 |  |
| Preventive Actions Measures to be taken | Mark off the zone, Prevent co-activities during transport of support structure from SX8 to UX85. |  |
| Personnel in charge of the realisation | Employees from the Physikalische Institut/Heidelberg and Nikhef/Amsterdam + Operators DBS for ponts roulants and movable platform. |  |
| Materials to be used | - Pont roulant available at SX8 (80 tons) - Ponts roulants available at UX85 (2x40 tons) - Movable platform (100 tons) |  |

1.2 - 	Method Statement

| Site:.Point 8......................................... . Work to be carried out: Installation of support structure of LHCb OT Trade:.......................................... Person Responsible Sebastian Bachmann |  | Form N° Written by Sebastian Bachmann. |
| --- | --- | --- |
| Work to be carried out WORK 2 | Installation of aluminium tables on concrete bunker. Figure 4 shows the position of the beton support in the LHCb experiment and the aluminium table in its final position. The table will be brought into its final position using the pont roulant and fixed by means of screws. |  |
| Risks | 1.) General risks of handling heavy loads. |  |
| Preventive Actions Measures to be taken | Mark off the zone. |  |
| Personnel in charge of the realisation | Employees from the Physikalische Institut/Heidelberg and Nikhef/Amsterdam + Operators DBS for ponts roulants and movable platform. |  |
| Materials to be used | Ponts roulants available at UX85 (2x40 tons) Movable platform (100 tons) |  |

1.3 - 	Method Statement

| Site:.Point 8......................................... . Work to be carried out: Installation of support structure of LHCb OT Trade:.......................................... Person Responsible Sebastian Bachmann |  | Form N° Written by Sebastian Bachmann. |
| --- | --- | --- |
| Work to be carried out WORK 3 | Erection of pillars to support OT bridge: Figure 5 shows the pillars in the final position. They are brought into their final position using the ponts roulant and are fixed by means of bolts. |  |
| Risks | - General risks of handling heavy loads. - General risks of working in height. |  |
| Preventive Actions Measures to be taken | Mark off the zone. |  |
| Personnel in charge of the realisation | Employees from the Physikalische Institut/Heidelberg and Nikhef/Amsterdam + Operators DBS for ponts roulants and movable platform. |  |
| Materials to be used | Ponts roulants available at UX85 (2x40 tons) Movable platform (100 tons) |  |

1.4 - 	Method Statement

| Site:.Point 8......................................... . Work to be carried out: Installation of support structure of LHCb OT Trade:.......................................... Person Responsible Sebastian Bachmann |  | Form N° Written by Sebastian Bachmann. |
| --- | --- | --- |
| Work to be carried out WORK 4 | Installation of OT bridge: Figure 6 shows the bridge in its final position. They are brought into their final position by the ponts roulant and are connected to the pillars by means of bolts. The fixation points for the crane are shown in Figure 3. The connection between the OT bridge and the pillars is done by means of bolts as shown in figure 3. |  |
| Risks | 1.) General risks of handling heavy loads. 2.) General risks of working in height. |  |
| Preventive Actions Measures to be taken | Mark off the zone. |  |
| Personnel in charge of the realisation | Employees from the Physikalische Institut/Heidelberg and Nikhef/Amsterdam + Operators DBS for ponts roulants and movable platform. |  |
| Materials to be used | Ponts roulants available at UX85 (2x40 tons). Movable platform (100 tons). |  |

Figure 1 Aluminium table, see also (LHS-100.dxf, LHS-120.dxf, LHS-130.dxf, LHS-140.dxf, LHS-150.dxf, LHS-160.dxf)

2 feet-

pillar

4 feet-

pillar

bridge

Figure 2 Bridge and pillars, see also drawing 05.200.69.0001.dwg

Figure 3 Fixation points for transport of bridge (in total 6x2 points for the entire bridge).

Figure 4 Aluiminium table on beton support

Pillars

RICH 2

Magnet

Figure 5 Pillars in the final position

Figure 6 Aluminium table, bridge and pillars in the final position.

Figure 4 :  Position of aluminium table on concrete support.

Figure 3 :  OT bridge