Task Procedure for ALICE

[ Task Procedure = simplified version of the Specific Plan for Health and Safety, adapted for ALICE Collaboration. - PPSPS = Plan Particulier de Sécurité et de Protection de la Santé ]

Task to be realized		Mounting of Readout Chambers

Location of work		SXL2

Dates of work		start 1.6.05			end  31.10.05

Sub-project	TPC				            Institute  GSI Darmstadt + Univ.HD

Sub-project Leader	Peter Braun-Munzinger	phone		71469

Safety link-person 	Peter Glassel			phone		16 3426

Work-Package Engineer Daniel Soyk		phone		16 3691

Local Work supervisor Peter Glassel		 	phone		16 3426

Experimental-Area Manager	Sébastien Evrard/Pieter Ijzermans	phone		16 4821

Persons involved	Uli Frankenfeld		task, qualification	physicist

Chilo Garabatos					physicist

Wolfgang Klempt					physicist

Joachim Baechler					physicist

Ingrid Kraus						physicist

Jean-Claude Labbe					technician

Borge S Nielsen					physicist

Anton Przybyla					technician

Rainer Renfordt					physicist

Hans-Rudolf Schmidt					physicist

Herbert Stelzer					physicist

Danilo Vranic						physicist

Jens Wiechula						physicist

Hansake Gustafsson					physicist

Brief description of work procedure

The 72 Readout Chambers will be installed on the TPC. For this purpose the TPC (sitting in the delphi frame) will be placed in the center of the cleanroom and the cleanroom walls and the roof will be closed.

The adapted elevating platform (LV152) will be placed in front of the TPC and the chambers are installed with a mounting tool that is placed on top of the platform.

The adapted platform will be checked by Safety Commission before using it in the cleanroom. A maximum of 5 people will be working on this platform.

The large readout chambers have a weight of  45 kg,  the small readout chambers have a weight of 20 kg.

During the entire chamber installation the cleanroom stays closed and no external crane from the hall is needed. Only when the platform is moved from one side of the TPC to the other we have to open the roof for 1-2 days.

The work will be done in two 6 hour shifts. Two chamber will be mounted per day.

| Detailed description (step by step) of the work procedure | Risk assessment | Preventive measures (collective), |
| --- | --- | --- |
| Lift Readout Chamber onto the platform (<=45 kg) | Work at height | Barrier on platform |
| Mount the Readout Chamber onto the installation tool | Work at height | Barrier on platform |
| Turn the installation tool to the correct angle | Work at height | Barrier on platform |
| Lift the platform the correct position | Work at height | Barrier on platform |
| Move the Readout Chamber inside the slot | Work at height | Barrier on platform |
| Mount the Readout Chamber in place | Work at height | Barrier on platform |
| Dismount the installation tool and start with the next Readout chamber | Work at height | Barrier on platform |

Responsibility

The Work-Package Engineer is responsible of this procedure.

The Work-Package Engineer and the Work-Package work supervisor certify that the persons involved have the proper qualifications and have been properly informed about safety aspects of the work.

WPE		……………………………..	 date	………………….

WPWS	……………………………..	 date	………………….

Approval

E.A.M. (also TSO)	Sébastien Evrard	date	…………...	...................................

16 4821

Safety Coordinator  	Emmanuel Paulat	date	…………...	………………………

16 3870

TS Transport Coord.	Jacky Bernard		date	…………...	………………………

16 0583

If needed, also sent to:

Integration & Installation Coordinator, 	Lars Leistam		16 0551

GLIMOS 					Marc Tavlet		16 0217 ou 70608

Commissioning Coordinator

(and Deputy Glimos),			Hans Taureg		16 0359

SC Inspector					Hervé Buret		16 0013

This task procedure must be on display at the place of work.