Task Procedure for ALICE

[ Task Procedure = simplified version of the Specific Plan for Health and Safety, adapted for ALICE Collaboration. - PPSPS = Plan Particulier de Sécurité et de Protection de la Santé ]

Task to be realized		Installation of TPC in Space Frame

Location of work		UX2

Dates of work		start 20.11.06			end  14.04.07

Sub-project	TPC				            Institute       GSI Darmstadt + Univ.HD

Sub-project Leader	Peter Braun-Munzinger	phone		71469

Safety link-person 	Peter Glassel			phone		16 3426

Work-Package Engineer Wolfgang Klempt		phone		16 0189

Local Work supervisor Yannick Lesenechal	 	phone		16 3349

Experimental-Area Manager	Sébastien Evrard/Pieter Ijzermans	phone		16 4821

Persons involved	Peter Braun-Munzinger	task, qualification	physicist

Peter Glassel						physicist

Wolfgang Klempt					physicist

Chilo Garabatos					physicist

Jean-Claude Labbe					technician

Yannick Lesenechal					technician

Andre Ferrand						technician

Antje Behrens						survey

Brief description of work procedure

The TPC in the DF is aligned to the SF. The DF and SF rails are connected by transfer rails. A first test movement of the TPC from the DF starting position to the IP is done while surveying the position and deformations of the system in small intervals. At the IP position, the TPC is realigned, if necessary. The ITS rail mount point at the absorbers is then adjusted. The TPC is then moved back to the ‘parking position’. The SF platform (between TPC and muon absorber and ITS platform (in front of the TPC inside the DF) are installed and ITS/beam line installation starts (separate work package). After the end of ITS installation, the TPC is moved to the IP, ITS installation is finalized.

| Detailed description (step by step) of the work procedure | Risk assessment | Preventive measures (collective), |
| --- | --- | --- |
| Alignment of DF and SF |  |  |
| Installation of transfer rails |  |  |
| Installation of part of SF platform and hydraulics for moving TPC |  |  |
| Moving the TPC to the IP |  |  |
| Alignment of the TPC at the IP |  |  |
| Insertion of one section o ITS rails and aligment at absorber |  |  |
| Prepare access and hydraulics for moving back |  |  |
| Move back TPC to parking position |  |  |
| ITS installation (separate work package) |  |  |
| Move TPC to IP |  |  |
| Complete ITS installation (separate work package) |  |  |

Responsibility

The Work-Package Engineer is responsible of this procedure.

The Work-Package Engineer and the Work-Package work supervisor certify that the persons involved have the proper qualifications and have been properly informed about safety aspects of the work.

WPE		……………………………..	 date	………………….

WPWS	……………………………..	 date	………………….

Approval

E.A.M. (also TSO)	Sébastien Evrard	date	…………...	...................................

16 4821

Safety Coordinator  	Emmanuel Paulat	date	…………...	………………………

16 3870

TS Transport Coord.	Jacky Bernard		date	…………...	………………………

16 0583

If needed, also sent to:

Integration & Installation Coordinator, 	Lars Leistam		16 0551

GLIMOS 					Marc Tavlet		16 0217 ou 70608

Commissioning Coordinator

(and Deputy Glimos),			Hans Taureg		16 0359

SC Inspector					Hervé Buret		16 0013

This task procedure must be on display at the place of work.