Task Procedure for ALICE

[ Task Procedure = simplified version of the Specific Plan for Health and Safety, adapted for ALICE Collaboration. - PPSPS = Plan Particulier de Sécurité et de Protection de la Santé ]

Task to be realized		Transport of TPC from SXL2 to UX2

Location of work		SXL2, PA2 yard, SX2, UX2

Dates of work		start 13.11.06			end  22.11.06

Sub-project	TPC				            Institute       GSI Darmstadt + Univ.HD

Sub-project Leader	Peter Braun-Munzinger	phone		71469

Safety link-person 	Peter Glassel			phone		16 3426

Work-Package Engineer Peter Glassel		phone		16 3426

Local Work supervisor Jean-Claude Labbe	 	phone		16 3361

Experimental-Area Manager	Sébastien Evrard/Pieter Ijzermans	phone		16 4821

Persons involved	Peter Braun-Munzinger	task, qualification	physicist

Peter Glassel						physicist

Wolfgang Klempt					physicist

Chilo Garabatos					physicist

Jean-Claude Labbe					technician

Yannick Lesenechal					technician

DBS

Friderici TS SA

Brief description of work procedure

The TPC is transported from its present location in the clean room in SXL2 to a position in front of the L3 magnet in UX2. The Delphi frame serves as the transport cradle. The details of the transport are described in the transport specification document at http://www.physi.uni-heidelberg.de/~glassel/TPC/TPC-transport/TPC-transport.pdf.

| Detailed description (step by step) of the work procedure | Risk assessment | Preventive measures (collective), |
| --- | --- | --- |
| Removing back wall and 3 parts of clean room roof |  |  |
| Set up hydraulic station and support beams in SX2 |  |  |
| Transport with SXL2 crane of TPC in Delphi frame from clean room to hydraulic station |  | Certified jig exists. |
| Lifting of TPC with hydraulic station |  |  |
| Transfer from hydraulic station to transport trailer |  |  |
| Trailer transport from SXL2 to SX2 |  |  |
| Transfer of TPC from trailer to hydraulic station |  |  |
| Lowering of TPC with hydraulic station |  |  |
| Transport with SX2 crane from hydraulic station to temp support in UX2 | Shaft grill needs to be removed | Temporary fence |
| Transfer of jig from SX2 crane to UX2 crane |  |  |
| Crane transport in UX2 to final support points before L3 magnet |  |  |

Responsibility

The Work-Package Engineer is responsible of this procedure.

The Work-Package Engineer and the Work-Package work supervisor certify that the persons involved have the proper qualifications and have been properly informed about safety aspects of the work.

WPE		……………………………..	 date	………………….

WPWS	……………………………..	 date	………………….

Approval

E.A.M. (also TSO)	Sébastien Evrard	date	…………...	...................................

16 4821

Safety Coordinator  	Emmanuel Paulat	date	…………...	………………………

16 3870

TS Transport Coord.	Jacky Bernard		date	…………...	………………………

16 0583

If needed, also sent to:

Integration & Installation Coordinator, 	Lars Leistam		16 0551

GLIMOS 					Marc Tavlet		16 0217 ou 70608

Commissioning Coordinator

(and Deputy Glimos),			Hans Taureg		16 0359

SC Inspector					Hervé Buret		16 0013

This task procedure must be on display at the place of work.