Task Procedure for ALICE

[ Task Procedure = simplified version of the Specific Plan for Health and Safety, adapted for ALICE Collaboration. - PPSPS = Plan Particulier de Sécurité et de Protection de la Santé ]

Task to be realized		Mounting of TPC-TRD heat screen

Location of work		SXL2

Dates of work		start 24.7.06			end  4.8.06

Sub-project	TPC				            Institute       GSI Darmstadt + Univ.HD

Sub-project Leader	Peter Braun-Munzinger	phone		71469

Safety link-person 	Peter Glassel			phone		16 3426

Work-Package Engineer Daniel Soyk		phone		16 3691

Local Work supervisor Peter Glassel		 	phone		16 3426

Experimental-Area Manager	Sébastien Evrard/Pieter Ijzermans	phone		16 4821

Persons involved	Daniel Soyk			task, qualification	engineer

Jean-Claude Labbe					technician

Thomas Morhardt					technician

Hans-Rudolf Schmidt					physicist	163962

Danilo Vranic						physicist

Thomas Morhardt					technician

Brief description of work procedure

The TPC-TRD heat screen is mounted on the inner surface of the Space Frame. An aluminium panel (light-weight) with cooling lines is mounted in each of the 18 x 5 rectangles, along the axial profiles, 18 water manifolds are mounted and connected to the panels.

Scaffolding on the inside of the Space Frame is needed for access. The first step is welding bolts  (bolt-welding machine) to the Space Frame, using a template for positioning. Then the panels are screwed onto some of the bolts, finally the manifolds, which further fix the panels, are put in place and bolted. The natural sequence would be to start on the top and equip sector by sector, gradually removing the scaffolding as one progresses downwards.

| Detailed description (step by step) of the work procedure | Risk assessment | Preventive measures (collective), |
| --- | --- | --- |
| Installation of scaffolding | Work at height | Professional job |
| Bring in bolt welding machine | Work at height | All work done from scaffolding |
| Attach template to axial beam | Work at height | .. |
| Weld bolts | Work at height | .. |
| Attach all panels of one sector | Work at height | .. |
| Mount the water manifold | Work at height | .. |
| Do pipe connections between panels and manifold | Work at height | .. |
| Vacuum test for leaks |  |  |
| Repeat sector by sector, removing scaffolding when necessary |  |  |

Responsibility

The Work-Package Engineer is responsible of this procedure.

The Work-Package Engineer and the Work-Package work supervisor certify that the persons involved have the proper qualifications and have been properly informed about safety aspects of the work.

WPE		……………………………..	 date	………………….

WPWS	……………………………..	 date	………………….

Approval

E.A.M. (also TSO)	Sébastien Evrard	date	…………...	...................................

16 4821

Safety Coordinator  	Emmanuel Paulat	date	…………...	………………………

16 3870

TS Transport Coord.	Jacky Bernard		date	…………...	………………………

16 0583

If needed, also sent to:

Integration & Installation Coordinator, 	Lars Leistam		16 0551

GLIMOS 					Marc Tavlet		16 0217 ou 70608

Commissioning Coordinator

(and Deputy Glimos),			Hans Taureg		16 0359

SC Inspector					Hervé Buret		16 0013

This task procedure must be on display at the place of work.